## Sheet1
Sub Project | Phase | Item | Remarks | Pic | Status | Percentage
API Server
Sprint #1

## Sheet2
Item | Value | Phase | Value | Remark | Requirement
SDM |  | Developing
| Project Manager |  | Perancangan Proses Bisnis dan Analisa Kebutuhan | Konsep Pembangungan Sistem, Flow Proses, Regulasi | Project Manager, System Analyst
| System Analyst |  | Perancangan Sistem | Context Diagram, UML Diagram, ERD, Database, UI/UX | Project Manager, System Analyst, Database Administrator, Web/Mobile Design
| Database Administrator |  | Coding |  | Project Manager, System Analyst, Database Administrator, Server Administrator, Programmer, Web/Mobile Design
| Server Administrator |  | Testing | Black Box Testing | Project Manager, System Analyst, Database Administrator, Server Administrator, Programmer, Tester
| Programmer Web |  | Publishing |  | Project Manager, System Analyst, Database Administrator, Server Administrator, Programmer, Tester
| Programmer IOS | Maintenance
Programmer Android
Tester
| Designer | Documentation
| Technical Writer |  | Pembuatan Dokumen Teknis Sistem
Infrastructure |  |  | Pembuatan Dokumen User Manual
Hosting Server
Domain
SSL

## Sheet2 (2)
COST STRUCTURE
No | Phase | Item | Month
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Developing
Perancangan Proses Bisnis dan Analisa Kebutuhan | bar: Month 1 to Month 2
Perancangan Sistem | bar: Month 1 to Month 2
Coding | bar: Month 3 to Month 6
2 | Implementation
Setup dan Instalasi
User Testing
Deployment
3 | Pelatihan & Sosialisasi | bar: Month 8
4 | Dokumentasi
Dokumen SRS | bar: Month 1 to Month 8
Dokumen Pengujian Sistem
Dokumen User Manual

## Sheet2 (3)
COST STRUCTURE
No | Requirement | Item | Jumlah | Durasi | Harga Satuan | Jumlah Harga
1 | Sdm
|  | Project Manager | 1 | 8
|  | System Analyst | 1 | 8
|  | Web/Mobile Designer | 1 | 8
|  | Database Administrator | 1 | 8
|  | Server Administrator | 1 | 8
|  | Programmer Web | 2 | 6 bln
|  | Programmer IOS | 1 | 6 bln
|  | Programmer Android | 1 | 6 bln
|  | Tester | 2 | 1 bln
|  | Technical Writer | 1 | 8 bln
Sub Total
2 | Infrastructure
|  | Hosting Server | 1 | 1 Thn
|  | Domain | 1 | 1 Thn
|  | SSL | 1 | 1 Thn
Sub Total
3 | Document
|  | Technical Document | 1
|  | User Manual Document | 1
Sub Total
Grand Total